## Regional Scoring
Table 4: Example of Regional Prioritization Evaluation and Scoring
ID | Framework Components | Screening and Scoring Methods |  |  | Inform. Not in Database | Project Database Information |  |  |  | Project Scoring Examples
[6 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
A.1 | Contribution to Planning Targets | Degree of Benefit
|  | H (6 pts) | M (4 pts) | L (2 pts)
A.1a1 | Improve Water Supply - Total (AFY) | >1000 | 100-1000 | <100 |  | 10000 | 1000 | - | 500 | 6 | 4 | - | 4
A.1b1 | Improve Water Quality* – (MGD) | >10 | 1-10 | <1 |  | - | 5 | - | 1.5 | - | 4 | - | 0*
A.1b2 | Groundwater* (AFY) | >1000 | 100-1000 | <100 |  | - | - | - | 1500 | - | - | - | 6
A.1c | Enhance Habitat (AC) | >10 | 1-10 | <1 |  | - | - | 0.1 | 10 | - | - | 2 | 4
A.1d1 | Enhance Open Space, Recreation (AC) | >10 | 1-10 | <1 |  | - | - | 0.5 | 5 | - | - | 2 | 4
| Subtotal | Out of 24 | [6 empty] | Subtotal | 6 | 8 | 4 | 18
A.2 | Other Regional Priorities | Yes/No Scoring
Y = 5 pts
A.2a | Multiple Sub-regions / Multiple Entities |  | Y/N |  |  | - | ü |  |  | - | 5 | - | -
A.2b | High Profile / Demonstration Project |  | Y/N |  | X | ü** |  |  | ü** | 5 | - | - | 5
| Subtotal | Out of 10 | [6 empty] | Subtotal | 5 | 5 | 0 | 5
| TOTAL | Out of 34 | [6 empty] | TOTAL | 11 | 13 | 4 | 23
* | Each project can be awarded points for either A.1b1 (Improve Water Quality) or A.1b2 (Groundwater), whichever is greater. For example, Project 4 has quantitative benefits for both criteria but is only awarded 6 points (not 6+4=10 pts)
** | Subjective Assessment by Leadership Committee
H/M/L | High, medium, and low category, with associated points
Y/N | Yes or no; associated points are all or nothing

## Sub-Regional Scoring
Table 6: Example of Sub-regional Prioritization Evaluation and Scoring
ID | Framework Components | Screening and Scoring Methods |  | Inform. Not in Database | Project Database Information |  |  |  | Project Scoring
[5 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
B.1 | Prioritized Objectives Sub-Regions: Rank Objectives | Weighted Yes/No Scoring
Rank (Wt.)
B.1a | Improve Water Supply | Y/N | 1 (8 pts) |  | ü | ü |  | ü | 8 | 8 | - | 8
B.1b | Improve Water Quality | Y/N | 2 (7 pts) |  |  | ü |  | ü | - | 7 | - | 7
B.1c | Enhance Habitat | Y/N | 3 (6 pts) |  |  |  | ü | ü | - | - | 6 | 6
B.1d | Enhance Open Space, Recreation | Y/N | 4 (5 pts) |  |  |  | ü | ü | - | - | 5 | 5
B.1e | Sustain Communities | Y/N | 5 (4 pts) | X |  |  |  | ü | - | - | - | 4
| Subtotal | Up to 30 | [5 empty] | Subtotal | 8 | 15 | 11 | 30
B.2-B.4 | Other Sub-Regional Priorities Sub-Regions: Choose Priorities (max 5) | Yes/No Scoring
Y=4, N=0
B.2 | Critical Needs | Y/N |  | X | ü |  |  | ü | 4 | - | - | 4
B.3 | Disadvantaged Communities | Y/N |  |  |  | ü |  | ü | - | 4 | - | 4
B.4a | [EX] Water Conservation Project Bonus | Y/N |  |  |  |  | ü |  | - | - | 4 | -
B.4b | [EX] Wetland Project Bonus | Y/N |  |  |  |  | ü |  | - | - | 4 | -
B.4c | [EX] Small Project Bonus (< $5M) | Y/N |  |  | $100M | $50M | $1.5M | $25M | - | - | 4 | -
| Subtotal | Out of 20 | [5 empty] | Subtotal | 4 | 4 | 12 | 8
| TOTAL | Out of 50 | [5 empty] | TOTAL | 12 | 19 | 23 | 38
Notes:
1. | Ranking of project alternatives allows each sub-region to emphasize (weight) different types of projects that the sub-region prefers.
2. | Points are awarded for each criterion based on the ranking assigned by the sub-region. The points range was set up so that the lowest priority objective would receive half points of the highest ranked abjective.
3. | Sub-regional priorities are up to five items selected by each sub-region to be evaluated on a yes/no basis.
[EX] | Example criteria are to be developed by each steering committee.
Y/N | Yes or no; associated points are all or nothing

## Readiness to Proceed Scoring
Table 8: Readiness to Proceed Prioritization Evaluation & Scoring
ID | Framework Components | Screening and Scoring Methods |  |  |  | Inform. Not in Database | Project Database Information |  |  |  | Project Scoring Examples
[7 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
C.1 | Documentation Progress | Degree of Completeness
|  | H (6 pts) | M (3 pts) | L (0 pts) | N/A **
C.1a | Conceptual Plans | C | IP | NI | NA |  | C | C | IP | NI | 6 | 6 | 3 | 0
C.1b | Land Acquisition | C | IP | NI | NA |  | C | IP | IP | NI | 6 | 3 | 3 | 0
C.1c | Preliminary Plans | C | IP | NI | NA |  | C | C | IP | NI | 6 | 6 | 3 | 0
C.1d | Permits | C | IP | NI | NA |  | C | IP | IP | NI | 6 | 3 | 3 | 0
C.1e | Construction Drawings | C | IP | NI | NA |  | C | IP | NI | NI | 6 | 3 | 0 | 0
| Subtotal | Out of 30 | [7 empty] | Subtotal | 30 | 21 | 12 | 0
C.2-C.5 | Feasibility, Cost, Schedule, & Support | Defined Benchmarks
|  | H (5 pts) | M (3 pts) | L (1 pt) | N/A **
C.2 | Project Feasibility (0-3 Documents) | 3+ | 2 | 1 | NA |  | 3 | 2 | 2 | 1 | 5 | 3 | 3 | 1
C.3 | Cost-Share | >60% | 40-60% | <40% | NA | X | 80% | 50% | 30% | 50% | 5 | 3 | 3 | 3
C.4 | Schedule – Construction Start | 2008-10 | 2011-12 | 2013+ | NA |  | 2009 | 2011 | 2010 | 2013 | 5 | 3 | 5 | 1
C.5 | Local Support | H | M | L | NA | X | L | H | M | H | 1 | 5 | 3 | 5
| Subtotal | H: Out of 20; H: Subtotal | 16 | 14 | 14 | 10
| TOTAL | H: Out of 50; H: TOTAL | 46 | 35 | 26 | 10
Notes:
** | Criteria not currently included in Project Database
C | Complete
H/M/L | High, medium, and low category, with associated points
IP | In Process
NI | Not Initiated
NA | Not Applicable

## Summary Scores
Table 9: Summary Scores for Each Project
Project ID | Regional Benefit |  | Sub-Regional Priorities |  | Readiness to Proceed
| Score | Rank | Score | Rank | Score | Rank
Project 1 | 11 | 3 | 12 | 4 | 46 | 1
Project 2 | 13 | 2 | 19 | 3 | 35 | 2
Project 3 | 4 | 4 | 23 | 2 | 26 | 3
Project 4 | 23 | 1 | 38 | 1 | 10 | 4